## project
Project Planner
[7 empty] | Period Highlight: |  |  |  |  | 43 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
| ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1 | Final Script Writing | 1 | 12 |  |  | 0%
2 | Physics Engine Coding | 1 | 5 |  |  | 0%
3 | Parkour Engine Coding | 1 | 4 |  |  | 0%
4 | Player Coding | 3 | 2 |  |  | 0%
5 | Player 3-D Modeling | 4 | 2 |  |  | 0%
6 | Player SFX | 4 | 2 |  |  | 0%
7 | GUI Coding | 4 | 3 |  |  | 0%
8 | GUI 2D-Art | 5 | 3 |  |  | 0%
9 | GUI SFX | 6 | 2 |  |  | 0%
10 | Combat Engine Coding | 7 | 4 |  |  | 0%
11 | Combat SFX | 8 | 3 |  |  | 0%
12 | Enemy AI Coding | 9 | 5 |  |  | 0%
13 | Enemy 3-D Modeling | 9 | 5 |  |  | 0%
14 | Enemy SFX | 10 | 4 |  |  | 0%
15 | Screen/Window/Menu/s Coding | 11 | 5 |  |  | 0%
16 | Screen/Window/Menu/s 2-D Art | 12 | 4 |  |  | 0%
17 | Screen/Window/Menu/s SFX | 13 | 3 |  |  | 0%
18 | Final Script Editing | 13 | 8 |  |  | 0%
19 | NPC/Citizen AI Coding | 14 | 5 |  |  | 0%
20 | Lower City NPC/Citizen 3-D Modeling | 14 | 5 |  |  | 0%
21 | Lower City NPC/Citizen SFX | 15 | 4 |  |  | 0%
22 | Mepsto's Junk Yard Assest Coding | 17 | 5 |  |  | 0%
23 | Mepsto's Junk Yard Assest Modeling | 18 | 4 |  |  | 0%
24 | Mepsto's Junk Yard Assest SFX | 19 | 3 |  |  | 0%
25 | Lower City Assest Coding | 22 | 5 |  |  | 0%
26 | Lower City Assest Modeling | 22 | 5 |  |  | 0%
27 | Lower City Assest SFX | 23 | 4 |  |  | 0%
28 | Upper City Assest Coding | 27 | 5 |  |  | 0%
29 | Upper City Assest Modeling | 27 | 5 |  |  | 0%
30 | Upper City Assest SFX | 28 | 4 |  |  | 0%
31 | Finalizing Mission Structure | 32 | 5 |  |  | 0%
32 | Effects/Lighting Engine Code | 32 | 6 |  |  | 0%
33 | Open World Coding | 32 | 8 |  |  | 0%
34 | Open World Modeling | 32 | 8 |  |  | 0%
35 | Casting Call for Voice Actors | 40 | 3 |  |  | 0%
36 | Mission/s Coding | 40 | 5 |  |  | 0%
37 | Mission/s Implemention | 40 | 3 |  |  | 0%
38 | Multiplayer Coding | 43 | 6 |  |  | 0%
39 | Multiplayer GUI | 43 | 3 |  |  | 0%
40 | Implement Voice Lines | 45 | 2 |  |  | 0%
41 | Create Open Beta Version | 49 | 6 |  |  | 0%
42 | Release Open Beta Version | 55 | 1 |  |  | 0%
43 | Fix bugs | 56 | 2 |  |  | 0%
44 | Release Final Game | 58 | 1 |  |  | 0%