## project
Project Planner
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Final Script Writing | 1 | 5 | 1 | 4 | 25%
Physics Engine Coding | 1 | 6 | 1 | 6 | 100%
Parkour Engine Coding | 2 | 4 | 2 | 5 | 35%
Player Coding | 4 | 8 | 4 | 6 | 10%
Player 3-D Modeling | 4 | 2 | 4 | 8 | 85%
GUI Coding | 4 | 3 | 4 | 6 | 85%
GUI 2D-Art | 5 | 4 | 5 | 3 | 50%
Combat Engine Coding | 5 | 2 | 5 | 5 | 60%
Enemy AI Coding | 5 | 2 | 5 | 6 | 75%
Enemy 3-D Modeling | 6 | 5 | 6 | 7 | 100%
Player and Enemy SFX | 6 | 1 | 5 | 8 | 60%
Screen/Window/Menu Coding | 9 | 3 | 9 | 3 | 0%
Screen/Window/Menu 2-D Art | 9 | 6 | 9 | 7 | 50%
Screen/Window/Menu SFX | 9 | 3 | 9 | 1 | 0%
Final Script Editing | 9 | 4 | 8 | 5 | 1%
NPC/Citizen AI Coding | 10 | 5 | 10 | 3 | 80%
Lower City NPC/Citizen 3-D Modeling | 11 | 2 | 11 | 5 | 0%
Mepsto's Junk Yard Assest Coding | 12 | 6 | 12 | 7 | 0%
Mepsto's Junk Yard Assest Modeling | 12 | 1 | 12 | 5 | 0%
Effects/Lighting Engine Code | 14 | 5 | 14 | 6 | 0%
Lower City Assest Coding | 14 | 8 | 14 | 2 | 44%
Lower City Assest Modeling | 14 | 7 | 14 | 3 | 0%
Upper City Assest Coding | 15 | 4 | 15 | 8 | 12%
Upper City Assest Modeling | 15 | 5 | 15 | 3 | 5%
Finalizing Mission Structure | 15 | 8 | 15 | 5 | 0%
Open World Coding | 16 | 28 | 16 | 30 | 50%
Open World Modeling | 16 | 28 | 16 | 30 | 50%
Mission/s Coding | 16 | 28 | 16 | 30 | 50%
Mission/s Implemention | 16 | 28 | 16 | 30 | 50%
Extra Character Modeling | 16 | 28 | 16 | 30 | 50%
Remaining SFX | 16 | 28 | 16 | 30 | 50%
| 16 | 28 | 16 | 30 | 50%